## SIR
UNDP
SITE INSPECTION REPORT
CONTRACTOR |  |  | SITE / SITE # |  |  |  | DATE
LLC"Avega" |  |  | Kyiv region, SP 28-32-8, Borodyanka, Semashka str., 3. |  |  |  | 2025-11-04
CONTRACTOR'S REPRESENTATIVE |  |  | M4H QA STAFF |  |  |  | MCTD REPRESENTATIVE
- |  |  | 1 |  |  |  | 1
SKILLED LABOR | UNSKILLED LABOR |  | MANAGEMENT ON SITE |  |  |  | WEATHER CONDITIONS
3 | 8 |  | 2 |  |  |  | rainy, +10*С
ONGOING ACTIVITIES
BLOCK / LOCATION | DESCRIPTION OF WORK (PER BOQ ITEM) |  |  |  |  | PER SCHEDULE? |  | REMARKS
indoor | Water supply system installation. |  |  |  |  | yes
| Heating system installation. |  |  |  |  | yes
| Electrical system installation. |  |  |  |  | no
| Sewerage system installation. |  |  |  |  | yes
outdoor | Roof installation. |  |  |  |  | no
| Walls insulation. |  |  |  |  | no
OBSERVANCES ON ONGOING ACTIVITIES
Installation of cold and hot water supply pipes in insulation tubes.
Installation heating system pipes in insulation tubes.
Heating radiators installation with thermostatic valves.
Installation of electrical cables in corrugated pipe.
Junction boxes installation.
Installation of wooden elements of the roof frame.
Installation of insulation mineral wool plates on the wall along axes A and 4.
IHP equpment installation.
OBSERVANCES ON HEALTH & SAFETY
[6 empty] | YES/NO |  | COMMENTS
All workers wear PPE equipment as relevant. | [5 empty] | yes
The fire shield / firefighting equipment is present at site. | [5 empty] | yes
The site is appropriately fenced. | [5 empty] | no |  | Part of fence was dismantled.
There is lavatories on the site. | [5 empty] | yes
There are safety briefing logs. | [5 empty] | yes
Safety information plate is in tact. | [5 empty] | yes
Scaffolding equipment have not secuerily base. | [7 empty] | must be made and installed in accordance with clause 7.3 of DBN A.3.2-2-2009.
IC drew attantion on the using temporary wiring on the site.
NARRATIVE ASSESSMENT - COMMENTS ON QUALITY
WORK | COMMENTS ON QUALITY |  |  |  | RECTIFICATION REMARKS (NNC / NTC) |  |  | STATUS OF RECTIFICATION
PURCHASED MATERIALS
MATERIALS AND EQUIPMENT | CHARACTERISTICS |  |  |  | PER DED? (yes/no) |  |  | NOTES
Plaster | Ceresit CT29 |  |  |  | yes
Mineral wool plate | Rokwool |  |  |  | no
Glue for mineral wool plates | Ceresit CT190 |  |  |  | yes
NARRATIVE ASSESSMENT - COMMENTS ON PROGRESS | [7 empty] | SCHEDULE REVISION REMARKS
Construction works is carried out slightly behind the Schedule. | [7 empty] | IC recommends increasing the quantity of workers, especially skilled labor to keep up with the Schedule.
M4H QA STAFF
NAME |  | TITLE |  | DATE |  | SIGNATURE
Pawel Neugebauer |  | TL IC |  | 2025-11-04
Report can be filled in electronically, no signature needed. | [8 empty] | END OF REPORT

## Photo Attachment
Installation wooden elements of the roof frame.
Installation wooden elements of the roof frame.
Facade insulation.
Facade insulation.
Facade insulation.
IHP equpment installation.
Installation of sewer, cold and hot water pipes.
Installation of sewer, cold and hot water pipes.
Installation of cold water pipes.
Heating system installation.
Installation electrical cables in corrugated pipe.
Purchased materials.
Anchoring floor slabs to each other.
Depth of slab support.
Purchased materials.
The fire shield is fully equipped. Lavatory on the site.
Garbage cans.
The gap between floor slab and partition have to be at least 2cm.
Scaffolding equipment must be made and installed in accordance with DBN.
Installation of concrete lintels should be done on top of a row of bricks..
Plumbing equipment installation.
Pipes needs additional fixation.
Waterproofing mortar layer have to be repair before tiles installation.
Waterproofing tape have to be repair before tiles installation.
Not filled seams between tiles.